Details on Monitoring and Evaluation, Impact Assessment Plan.

Need for Monitoring, Evaluation & Impact Assessment system for the MDM Programme

In order to improve the program efficiency and overall impact of the MDMP, the National Programme of Nutritional Support to Primary Education (NPNSPE) Guidelines (2006, p.31-32) specifies that

The Mid-Day Meal Programme needs to be monitored to assess:

Programme parameters, namely the manner in which the programme is being implemented in terms of all children regularly getting a meal of satisfactory quality, and

Impact parameters, namely the effect, if any, on improving children’s nutritional status, regularity of attendance, and retention in and completion of Primary Education.

The NPNSPE guidelines 2006, has stipulated provisions and mechanisms for Centre, States & Districts to monitor & evaluate the programme at stated frequency. As mandated in the guidelines, SMC (School Monitoring Committee) has an active role to play in the monitoring of the programme at block level. The NPNSPE guidelines 2006, Annexure-12, p.79 provides details of the monitoring of programme and impact parameters. The annexure specifies the responsible agencies such as authorities from the central government, state government, local administrative heads, teachers and nutrition experts and the frequency of monitoring of the following parameters:

- Regularity and wholesomeness of mid-day meal served to children

- Promoting social and gender equity

- Cleanliness in cooking, serving and consumption of mid-day meal

- Timely procurement of Ingredients, fuel, etc. of good quality

- Implementation of varied menu

- Over-all quality of Mid-Day Meal

- Nutritional Status – assessment of percentage of underweight children and incidences of anaemia

- Attendance Status

- Retention/Completion Status

For monitoring & evaluation of the MDM programme, the government provides an additional Management, Monitoring & Evaluation (MME) cost.  Para 5 of the Meal Section page of the Mid Day Meal scheme website states: “Provide assistance to States/ UTs for Management, Monitoring & Evaluation (MME) at the rate of 1.8% of total assistance on (a) free food grains, (b) transport cost (c) cooking cost and (d) Honorarium to cook-cum-helpers.” (http://mdm.nic.in/Meal%20Provision.html).

Thus, the government has initiated necessary steps to ensure the effective programme management of the MDM.

A rudimentary review of literature on mid-day meals in India reveals that several studies have been conducted in different parts of our country to measure the impact of mid-day meal on school enrolment rate, attendance rate, school dropout rate, academic performance and health and nutritional status. For instance, an impact assessment study on MDM conducted by Nambiar, Desai, Patel and Roy (2012) in schools of rural Vadodara states that

The MDMP has shown partial success in encouraging enrolment for the disadvantaged section. However, the actual number of beneficiaries is still less from expectation due to various reasons such as monotonous recipes, poor quality of raw ingredients, lack of palatability and organoleptic qualities. Considering the infrastructure and facilities available, 50% schools adhered to the norms of NP-NSPE guidelines. Improving the logistics and facilities in the schools could help in improving the quality of MDM served as well as adhering to the cyclic menu thereby fulfilling the nutritional quality and quantity of the programme. Amended perceptions, developing positive attitude and improved capacity building of the school teachers as well as the MDM staff would be possible by repetitive training programmes. The nutritional status of the children has revealed high prevalence of micronutrient deficiencies, highlighting on the deficit of the micronutrient consumption, unhygienic cooking conditions and high prevalence of infection. Thus there is a need to augment seasonal vegetables, improve the sanitation and hygiene conditions during food handling and undergo some treatment of disinfection for the children.

Mid-Day meal programme has a positive influence on the health & nutrition status of the child as shown by a study conducted by Minj, Goud, James, Furruqh and Mohammad (2014, p. 83) to assess the impact of MDM on nutritional status of the children living in the rural area of South Karnataka. The study concludes that

the introduction of MDM there was a reduction in the proportion of children with stunting as well as a reduction in the proportion of children with both grades 3 and 4 under nutrition. Also,  under nutrition among girls was high both before and after the introduction of MDM. And thirdly, the percentage improvement in the nutritional status after the introduction of MDM was more among girls when compared to boys in a majority of the age groups.

These studies show that the regular monitoring, evaluation and impact assessment of the MDMP can result in the identification of the benefits and the gaps of the programme thus leading to continuous improvement efforts.

The Akshaya Patra Foundation, as an implementing agency of MDMP across various states in India, has been focussing on the cooking & delivery of MDM in various government and government- aided schools since 18 years. As an implementing agency, the organisation focusses primarily on the food safety, infrastructure, quality assurance & nutrition compliance aspects during the cooking and delivering of the meals to schools, adhering to the standards mentioned in the FSSAI Act and mandated rules for the civil society organisations as per the agreements with the government.

Additionally, in self-driven initiatives that go beyond the stated expectations of the government, the NGO has conducted scientific impact assessment studies in the beneficiary schools by commissioning reputed agencies such as Nielsen and Manipal University.

The impact assessment study conducted by Nielsen (2010, p.2-3) reported that while there was an improvement in enrolment and attendance rates there was no significant improvement in dropout rates and scholastic abilities. The impact on nutritional status showed that over 40% of students were underweight.

The study conducted by Kamath, Achar and Shetty (2012, p.5-6) focussed on measuring the impact of MDM on child growth reported an overall prevalence of malnutrition among students to be 28%. Among them 19% were undernourished and 9% were found to be overweight/obese. There were region wise variations. In Bellary the prevalence malnutrition among children was high (33%), then followed by Hubli (26%). In Mangalore and Mysore the prevalence of malnutrition among children was found to be low. The attributing factors could be income status of the family, eating habits, awareness and literacy among parents etc. However, this needs to be studied further. The general examination of children done by doctor revealed that 31% of children had dental caries, 8% children showed symptoms of pallor. The other common symptom reported was Vitamin A Deficiency among children. The nutrition status of children receiving mid-day meals from TAPF was good as compared to with the studies done on the nutrition status other students.

Therefore, it can be concluded that a systematic monitoring, evaluation and impact assessment (ME&IA) system is the need of the hour to achieve the objectives of the MDMP. Such a system will enable internal assessment of the impact of MDM by the NGOs, identification and implementation of improvement actions thus leading to sustained actions towards child development and programme effectiveness.

Akshaya Patra aims at developing a simple and effective ME&IA system and to deploy it across all its centres. After successful implementation, the model could be replicated by other NGOs engaged in school feeding programme.

MANDATORY STIPULATION AS PER MID- DAY MEAL GUIDELINES (2006)

The Mid-Day Meal Programme needs to be monitored to assess:

- Programme parameters, namely the manner in which the programme is being implemented in terms of all children regularly getting a meal of satisfactory quality, and

- Impact parameters, namely the effect, if any, on improving children’s nutritional status, regularity of attendance, and retention in and completion of Primary Education.

THE NEED FOR AKSHAYA PATRA – FOR MONITORING, EVALUATING & IMPACT ASSESSMENT OF MID-DAY MEAL PROGRAMME (MDMP)

- The Akshaya Patra Foundation, as an implementing agency of MDMP across various states in India, has been focussing on the cooking & delivery of MDM in various government and government- aided schools since 18 years.

- As an implementing agency, the organisation focusses primarily on the food safety, infrastructure, quality assurance & nutrition compliance aspects during the cooking and delivering of the meals to schools, adhering to the standards mentioned in the FSSAI Act and mandated rules for the civil society organisations as per the agreements with the government.

- Thus, for the organization to take a methodical step towards strengthening the efficacy of the Mid-Day Meal Programme & make it  sustainable for child growth , it is essential to develop a systematic monitoring, evaluation and impact assessment (ME&IA) system.  This system shall aid the organization in achieving the objectives of the MDMP.

Akshaya Patra aims at developing a simple and effective ME&IA system and to deploy it across all its centres. After successful implementation, the model could be replicated by other NGOs engaged in school feeding programme.

Such a system will enable internal assessment of the impact of MDM by the NGOs, identification and implementation of improvement actions thus leading to sustained actions towards child development and programme effectiveness.

ON-GOING EFFORTS FOR MDM MONITORING & EVALUATION

Currently, the impact of MDMP is measured by:

- Mid-Day Meal Policy Evaluation:

- To acknowledge the gaps in the existing MDM program

•  To advocate the need to address the existing gaps in the implementation of MDM program to various stakeholders

•  Liaison with the government agencies to revise the policy of MDM programme

•  To bridge all the gaps in the existing MDM system and build a holistic policy that covers the revised health & nutrition parameters

2. Health & Nutrition Framework

- To Assess health and nutrition study of Akshaya Patra’s Mid-day

•  To streamline the impact assessment process as far as health and nutrition assessments are concerned in India

•  To derive areas of improvement in mid-day meal mechanism and provide base for advocacy

MONITORING & EVALUATION PLAN

|  | PROGRAMME INDICATORS | TARGET What is the Target Value | FREQUENCY How often will it be measured | RESPONSIBILITY Who will measure it | REPORTING Where will it be reported |
| --- | --- | --- | --- | --- | --- |
| Goal-1 | Regularity and wholesomeness of mid-day meal served to children | Daily Tracking with maintained temperature | Daily | (i)Representatives of Gram Panchayats/ Gram Sabhas (ii) Members of Committee of Mothers/VEC/PTA/SMDC (iii) Teachers (iv) Third Party Evaluators | District/Block Level Organization Level Reports for all Stakeholders involved |
| Goal-2 | Cleanliness in cooking, serving and consumption of midday meal | Permitted Bacterial Counts at Cooking & Serving Place. Zero Food Wastage | Daily | (i)Representatives of Gram Panchayats/ Gram Sabhas (ii) Members of Committee of Mothers/VEC/PTA/SMDC (iii) Teachers (iv) Third Party Evaluators | District/Block Level Organization Level Reports for all Stakeholders involved |
|  | PROGRAMME INDICATORS | TARGET What is the Target Value | FREQUENCY How often will it be measured | RESPONSIBILITY Who will measure it | REPORTING Where will it be reported |
| Goal-3 | Timely procurement of Ingredients, fuel, etc. of good quality | Procured Ingredients with Agmarks & BSI’s. Stocks procured before ending shelf-life | Weekly | (i)Representatives of Gram Panchayats/ Gram Sabhas (ii) Members of Committee of Mothers/VEC/PTA/SMDC (iii) Teachers (iv) Third Party Evaluators | District/Block Level Organization Level Reports for all Stakeholders involved |
| Goal-4 | Implementation of varied menu | Presence of all food groups in the MDM Menu | Fortnight /Monthly | (i)Gram Panchayat / Municipality / (ii) Representatives of Block-level SMC (iii) ) Third Party Evaluators | District/Block Level Organization Level Reports for all Stakeholders involved |
|  | PROGRAMME INDICATORS | TARGET What is the Target Value | FREQUENCY How often will it be measured | RESPONSIBILITY Who will measure it | REPORTING Where will it be reported |
| Goal-5 | Over-all quality of Mid-Day Meal | Zero bacterial contamination. 100 % Nutrition Compliance accredited through NABL labs. | Monthly | Officers of State Govt. belonging to Revenue/Administration, Rural Development, Education, Nodal Departments, and any other suitable Department (e.g. WCD, Food, Health, etc.) b. Officers of Food & Nutrition Board (FNB), Govt. of India, posted in the State/UT c. Nutrition Experts / Institutions identified / nominated by the State Govt. / Third Party Evaluators | District/Block Level Organization Level Reports for all Stakeholders involved |
| Goal-6 | Promoting social and gender equity |  | Daily | (i)Representatives of Gram Panchayats/ Gram Sabhas (ii) Members of Committee of Mothers/VEC/PTA/SMDC (iii) Teachers (iv) Third Party Evaluators | District/Block Level Organization Level Reports for all Stakeholders involved |
|  | PROGRAMME INDICATORS | TARGET What is the Target Value | FREQUENCY How often will it be measured | RESPONSIBILITY Who will measure it | REPORTING Where will it be reported |
| Goal-7 | Nutritional Status – assessment of percentage of underweight children at school level | Shift of Severe category children to Moderate Category and Moderate to Mild & Normal Categories | Quarterly | Nutrition Experts / Institutions identified / nominated by the State Govt. / Third Party Evaluators / Public Health – Community Medicine Doctors | District/Block Level Organization Level Reports for all Stakeholders involved. WHO Collaborating Centre |
| Goal-8 | Attendance Status | 100 % All school days | Quarterly | (i)Representatives of Gram Panchayats/ Gram Sabhas (ii) Members of Committee of Mothers/VEC/PTA/SMDC (iii) Teachers (iv) Third Party Evaluators | District/Block Level Organization Level Reports for all Stakeholders involved |
|  | PROGRAMME INDICATORS | TARGET What is the Target Value | FREQUENCY How often will it be measured | RESPONSIBILITY Who will measure it | REPORTING Where will it be reported |
| Goal-9 | Retention/Completion Status | 100% All school days | Annually | (i)Representatives of Gram Panchayats/ Gram Sabhas (ii) Members of Committee of Mothers/VEC/PTA/SMDC (iii) Teachers (iv) Third Party Evaluators | District/Block Level Organization Level Reports for all Stakeholders involved |
| Goal-10 | Assessment of Deficiency Diseases and Food Allergies | Absence of Deficiency diseases & Food Allergies. | Quarterly | Nutrition Experts / Institutions identified / nominated by the State Govt. / Third Party Evaluators / Public Health – Community Medicine Doctors | District/Block Level Organization Level Reports for all Stakeholders involved WHO Collaborating Centre |
|  | PROGRAMME INDICATORS | TARGET What is the Target Value | FREQUENCY How often will it be measured | RESPONSIBILITY Who will measure it | REPORTING Where will it be reported |
| Goal-11 | Feedback Mechanism | Monthly Feedback Reports based on Daily/Weekly Feedbacks | Daily | Research Team/ School Relation Officers/ Operations team/ Third Party Evaluators | Weekly & Monthly Feedback Reports at Organization Level |
| Goal-12 | Grievance Redressal | Twice in a Month | Daily Reporting | Research Team/ School Relation Officers/ Operations team/ Third Party Evaluators | Weekly & Monthly Grievance Reports at Organization Level |

MEASURING THE PROGRAMME INDICATORS OF MID-DAY MEAL PROGRAMME

| PROGRAMME INDICATORS | DATA SOURCE How will it be measured |
| --- | --- |
| Regularity and wholesomeness of mid-day meal served to children | Observation methods, Qualitative Questionnaire & checking school registers for MDM |
| Cleanliness in cooking, serving and consumption of midday meal | Observation methods, Qualitative Questionnaire & checking school registers for MDM |
| Timely procurement of Ingredients, fuel, etc. of good quality | Observation methods, Qualitative Questionnaire & checking school registers for MDM |
| Implementation of varied menu | Observation methods, Qualitative Questionnaire & checking school registers for MDM, Feedbacks from Beneficiaries |
| Over-all quality of Mid-Day Meal | Observation methods, Qualitative Questionnaire & checking school registers for MDM, Feedbacks from Beneficiaries, NABL Lab reports |
| Promoting social and gender equity | School Registers |
| Nutritional Status – assessment of percentage of underweight children at school level | Anthropometric Assessments & Qualitative Questionnaires |
| Attendance Status | School Registers |
| Retention/Completion Status | School Registers |
| Assessment of Deficiency Diseases and Food Allergies | Qualitative Questionnaires, Assessment of clinical signs & symptoms through non-invasive techniques |

IMPACT ASSESSMENT PLAN- MID-DAY MEAL PROGRAMME

Impact assessment plan with project cycle

Impact Assessment Plan

Project Cycle

Detail plan- Level 1 Matrix

| Level 1 matrix Process flow |  |  |  |
| --- | --- | --- | --- |
| A. Initial Analysis | B. Concept design | C. Planning and designing study | D. Baseline survey |
| - Literature, - Needs assessments studies, - Feasibility studies, - Participatory rapid appraisals (PRAs), - Community mapping and studies, - SWOT (strengths, weaknesses, opportunities, threats) analysis | - Goal - Outcomes Output - Activities - Inputs | - Study indicators - Methods - Frequency and sample - Person responsible - Data analysis - Training data collectors and evaluators - Address ethical concerns and permissions | - Secondary data. - Sample surveys - Qualitative study - Quantitative study - Participatory assessment |

Detail plan- Level 2 Matrix

| Level 2 Matrix Process flow |  |
| --- | --- |
| A. Project Monitoring | B. Mid-term Evaluation |
| - SWOT (strengths, weaknesses, opportunities, threats) analysis - Checklists - Comparing project outcome, activities and inputs with actuals | - Comparing project deadlines with actuals - Disseminating the assessment outcome - Need assessment for any other further addition or change in the project. |

Detail plan- Level 3 Matrix

| Level 3 Matrix Process flow |  |
| --- | --- |
| A. Final Evaluation ( with end line survey) | B. Disseminating results for further planning |
| - End-line survey - Checklists indicators if there is any change at level 2 - Comparing project outcome, activities and inputs with actuals - Data Analysis report to be published | - Impact assessment reports on the indicators analyzed during the project life cycle. - Disseminating results and analyzing further project based on findings. |